## Proj file
Country | VIETNAM
PROJECT NAME | CAPACITY DEVELOPMENT FOR PLANNING REFORM
PROJECT CODE | VIE 1204811
INTERVENTION ZONE | GOVERNANCE
BUDGET | 4,000,000 EUR
PARTNER INSTITUTION | MINISTRY OF PLANNING AND INVESTMENT
DATE OF SPECIFIC AGREEMENT | 11.4.2014
PROJECT END | 4.2018
EXPIRY SPEC AGR | 4.2019
DURATION (MONTHS) | 48 MONTHS
TARGET GROUPS | MPI, line ministries, provinces and sub-provincial authorities, training insitutions
GO | To improve the preparation and implementation of the Socio-economic Development Plan through improved planning and budgeting for pro-poor and pro-growth policies and interventions
SOs | To strengthen the capacity of (selected) national and sub national governments in improved planning and budgeting
RESULTS | R1. The legal framework for the planning reform is improved
R2. The capacity of MPI to support capacity development of sub-national authorities in the area of planning and M&E is strengthened
R3. The capacity of provincial authorities and 2-3 line ministries to develop, adopt and implement improved planning and M&E systems is strengthened
R4. Thecapacity of selected local (districts+ communes) authorities to develop, adopt and implement improved planningand M&E systems is increased
PARAMETRES
YEAR OF REFERENCE | 2014 | Start at
QUARTER OF REFERENCE | Q1
Date | 10.10.2017
CONTENT
Organisation chart
Risk and issues management
Follow-up decisions JLCB
Procurement follow-up
Execution Agreements and Financing Agreements
Human Resources
Narrative
Operational planning & follow-up
POP excerpt
Monitoring & Evaluation matrix
Financial planning
Detailed financial planning.
Summary

## Risks Issues
PROJECT CODE | VIE 1204811
PROJECT NAME | CAPACITY DEVELOPMENT FOR PLANNING REFORM
YEAR OF REFERENCE | 2017
QUARTER OF REFERENCE | Q1
Identification of risk or issue |  |  | Analysis of risk or issue |  |  | Deal with risk or issue |  |  | Follow-up of risk or issue
Risk description | Period of identification | Category | Likelihood | Potential impact | Total | Action(s) | Resp. | Deadline | Progress | Status
Workload delay the start of the project activities (POM, baseline, capacity assessment) | Formulation | OPS | Medium | Low | Low Risk | Draft POM is available and under final review by PM | PMU | Q2 2105 | POM finalised and approved | Terminated
[6 empty] | Consultant for baseline was selected and starts work in July 2015 | PMU | Q4 | ensure completion of baseline in Q1, 2016
[6 empty] | Institutional and organisational capacity assessment of provinces in progress | PMU | Q4 2015 | ensure timely finalisation of the capacity assessment within Q1 2016
Heavy CDPR workload to support regulatory documents for the MTIP and SEDP 2016-2020. Many documents on PI and SEDP need to be prepared and disseminated on time | start up | DEV | Low | High | Medium Risk | DNEI and CDPR work hard to complete the documents and instructions on time | PMU |  | The regulatory framework for the SEDP 2016-2020 and the MTIP are completed | Terminated
Insert a line here
Delay in selection of the pilot provinces | start up | DEV | Low | Medium | Low Risk | CDPR undertook a visit to 4 of the 9 preselected provinces |  | asap | 5 concentration provinces selected and approved by PSC in july 2015 | Terminated
Next PSC will approve the selection of the provinces in Q3
Insert a line here
The CD approach remains focused on supply driven training for individual skills and not on organizational and institutional level | Formulation | DEV | Low | High | Medium Risk | undertake institutional and organizational capacity assessments as soon as provinces are selected |  |  | Capacity assessment ongoing and to be completed in Q1, 2016 Given the general situation and high levels ofrecent change in legal framework (PIL, SBL) supply driven staff training (dessemination is the number one priority. | Terminated
Execution rate slightly under target | Q3, 2015 | FIN | Medium | Medium | Medium Risk | 28% execution rate @ 40% of project duration | PMU |  | timely implementation of the 2016 plan which will bring the executon rate at 60% at the end of 2016 (66% of project duration) | Terminated
Insert a line here
implementation of results 4 with sub provincial authorities is delayed | Q4, 2015 | DEV | Medium | Medium | Medium Risk | identify areas of capacity development for district and communes from the capacity assessment | PMU | Q2, 2016 | The PSC approved the Decision relating to modification of TFF (adjusted the implementation method of activity A0401) | Terminated
Activity A0401 started to be implemented on December 2016
The high implementation target planned for 2017 is very ambitious | Q1, 2017 | FIN | Medium | Medium | Medium Risk |  |  |  |  | Terminated
[6 empty] | Actualise planning on basis of Q1 results | PMU | Q4,2017 | awaiting financial result Q1
Insert a line here
An acellerated implementation needs a detailed planning but could have a negative impact on quality and on the focus for consolidation | Q1, 2017 | DEV | Medium | Medium | Medium Risk |  |  |  |  | Terminated
the project director details planning of activities and quality control measures
Insert a line here
Insert a line here
Insert a line here
Insert a line here
Insert a line here
Insert a line here
Insert a line here
Insert a line here
Insert a line here
Insert a line here
Insert a line here
FIN
[11 empty] | Low | Limited | OP
[11 empty] | Medium | Moderate | DEV
[11 empty] | High | High | REP

## JLCB dec
| PROJECT CODE | VIE 1204811 |  |  |  | * | Source: | MTR, Backstopping, Audit, JLCB, JC
| PROJECT NAME | CAPACITY DEVELOPMENT FOR PLANNING REFORM | [5 empty] | Operational report, Results report
| YEAR OF REFERENCE | 2017 | [5 empty] | etc…
| QUARTER OF REFERENCE | Q2
| Decision |  |  |  | Action |  |  | Follow-up
N° | Decision | Identification period (mmm.yy) | Source* | Actor | Action(s) | Resp. | Deadline | Progress | Status
1 | The missing article 7.3 in the EN version of the SA needs to be corrected through an exchange of letter | 2014-09-24 | report |  | MPI will initiate exchange of letter |  |  |  | CLOSED
Insert a line here
2 | budget inconsistencies will be corrected by the PMU and submitted to the PSC | 2014-09-14 | report |  | PMU will correct inconsistencies and resubmit to PSC |  |  |  | CLOSED
Insert a line here
3 | PMU will seek clarifications from BTC on the budget revision | 2014-09-14 | report |  | PMU will seek clarifications from BTC on the budget revision |  |  |  | CLOSED
Insert a line here
4 | PMU will prepare an OWP to be submitted to the PSC | 2014-09-14 | report |  | OWP prepared and submitted |  |  |  | CLOSED
Insert a line here
5 | Baseline report needs to be finalised by the end of January 2016 | 2015-12-01 |  |  | PMU has been finalised and will soon be submitted to the PSC |  |  |  | CLOSED
Insert a line here
6 | Ensure timely implementation of plan 2016 to increase execution rate | 2015-12-01 |  |  | necessary budget revision will be included in 2016 workplan to be submitted to PSC |  |  |  | CLOSED
Insert a line here
7 | project car will not be purchased and funds move to training | 2015-12-01 |  |  | necessary budget revision will be included in 2016 workplan to be submitted to PSC |  |  |  | CLOSED
Insert a line here
8 | Workplan 2016 | 2016-02-01 | report | PMU | The PSC approved the WP2016 prepared by the PMU |  |  |  | CLOSED
Insert a line here
9 | Change the implementation method of activity A0401 | 2016-12-01 |  |  | The PSC approved the Decision relating to modification of TFF (adjusted the implementation method of activity A0401) |  |  |  | CLOSED
Insert a line here
10 | Workplan 2017 | 2017-03-16 |  |  | The PSC approved the WP2017 prepared by the PMU |  |  |  | CLOSED
Insert a line here
11 | Modification of OWP revised the budget for activity A0302 | 2017-05-01 |  |  | The PSC approved the modification of the financial plan of OWP |  |  |  | CLOSED
Insert a line here
12 | Modification of financial plan 2017 | 2017-05-01 |  |  | The PSC approved the modification of the financial plan of plan for 2017 |  |  |  | CLOSED
Insert a line here
13 | Modification of OWP revised the budget for activity Z0302 | 2017-06-17 |  |  | The PSC approved the modification of the financial plan of OWP |  |  |  | CLOSED
Insert a line here
14 | Modification of OWP revised the budget for activity Z0302 and others budget lines | 2017-10-17 | [6 empty] | CLOSED
Insert a line here
15 | budget modification march 2018 | 2018-03-01 |  |  | PSC approved budget modification |  | 2018-06-01 | 3 workshops planned in april, 2 workshops in Mai | ONGOING
Insert a line here
16
Insert a line here

## Plan Op
|  | PROJECT CODE | VIE 1204811
PROJECT NAME: CAPACITY DEVELOPMENT FOR THE PLANNING REFORM
|  | YEAR OF REFERENCE | 2017
|  | QUARTER OF REFERENCE | Q4
[7 empty] | Q12014 |  |  | Q22014 |  |  | Q32014 |  |  | Q42014 |  |  | Q12015 |  |  | Q22015 |  |  | Q32015 |  |  | Q42015 |  |  | Q12016 |  |  | Q22016 |  |  | Q32016 |  | Q42016 |  |  | Q12017 |  |  | Q22017 |  |  | Q32017 |  |  | Q42017 |  |  | Q12018 |  |  | Q22018 |  |  | Q32018 |  |  | Q42018 |  |  | Status
TYPE | BUDGET CODE | DESCRIPTION | PL/UPD | Start | End | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-16 | 2016-02-16 | 2016-03-16 | 2016-04-16 | 2016-05-16 | 2016-06-16 | 2016-07-16 | 2016-08-16 | 2016-09-16 | 2016-10-16 | 2016-11-16 | 2016-12-16 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-17 | 2017-08-17 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-17 | 2018-08-17 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | Progress | FINDINGS/RECOMMENDATIONS / PLANNING
Result 1 |  | Legal framework developed and updated
Activity | A01-01 | Draft required legal and regulatory instruments | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 19300 | 9000 | 9000 | 10000 | 900 | 900 | 900 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 3100 | 3000 | 3000 | 4000 | 3000 | 3000 | 5145 | 3000 | 3000 | 5145 | 4000 | 4000 | 4290 | 25000 | 0 |  | 25000 |  |  | 5000 | 5000 | 10000 | 0 | 0 | 0
|  |  | Updated | [7 empty] | 19300 | 21285 | 20000 | 20000 | 4500 | 4500 | 4500 | 3000 | 3000 | 4000 | 10000 | 10000 | 15495 | 0 | 5989 | 0 | 1296 | 0 | 0 | 1000 | 1000 | 1676 | [6 empty] | 0 | 0 | 4624 | 25000 | 25000 | 3263 |  | 4120 |  |  |  | 22368 | 0 | 0 | 0
Activity | A01-02 | Issue MPI's circular(s) on national and sub-national planning | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4100 | 4900 |  |  |  | 3000 | 3000 | 3505 | 3000 | 3000 | 3505 | 3000 | 3000 | 3505 | 30000 | 0 |  | 12571 |  |  | 0 | 0 | 5000 | 0 | 0 | 0
|  |  | Updated | [8 empty] | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 2500 | 2500 | 3000 | 3000 | 4000 | 2500 | 2500 | 2500 | 13928 | 10000 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 2000 | 2000 | 4458 | 29727 |  |  | 2541 |  |  |  |  | 9805 | 0 | 0 | 0
Activity | A01-03 | Issue MPI's circular(s) on incentives to improved planning | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 |  |  |  | 0 | 0 | 3716 | 0 | 0 | 3716 | 0 | 0 | 3716 | [6 empty] | 0 | 14864 | 0 | 0 | 0 | 0
|  |  | Updated | [8 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 6000 | 0 | 6000 | 0 | 3000 | 3000 | 4000 | 12000 | 12000 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 0 |  |  | 14864 |  | 0 | 0 | 0
Activity | A01-04 | Workshops, seminars for monitoring alignment initiatives | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 2400 |  |  |  | 1000 | 1000 | 3000 | 5000 | 0 | 0 | 0 | 0 | 0 |  |  | 5000 | 5000 | [5 empty] | 0 | 0 | 0
|  |  | Updated | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1000 | 2000 | 2000 | 10000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  | 20085 | [5 empty] | 0 | 0 | 0
Activity | A01-05 | Review and update planning guidelines based on lessons | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 2400 |  |  |  | 0 | 0 | 0 | 5169 | 0 | 0 | 0 | 0 | 5169 |  |  | 3826 |  | 3826 |  |  |  | 20338 | 0 | 0 | 0
|  |  | Updated | [7 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  |  | 18754 | 0 | 0 | 0
Result 2 |  | Increased capacity of MPI to support CD of sub-national authorities
Activity | A02-01 | Develop shared understanding on support to CD | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 4000 | 3000 | 3000 | 4000 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 1200 |  |  |  | 2000 | 2000 | 3000 | 2000 | 2000 | 3000 | 2000 | 2000 | 2128 | [9 empty] | 0 | 0 | 0
|  |  | Updated | [11 empty] | 0 | 5000 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2965 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 342 | 0 | 0 | 166 | [9 empty] | 0 | 0 | 0
Activity | A02-02 | Carry out Capitalization Study on CD initiatives | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 1200 |  |  |  | 0 | 0 | 0 | 4523 | 0 | 0 | 1500 | 1500 | 1523 |  |  |  | 9046 |  |  |  | 0 | 9046
|  |  | Updated | [11 empty] | 0 | 5000 | 0 | 0 | 0 | 5000 | 3000 | 3000 | 4000 | 1000 | 2000 | 2000 | 0 | 11219 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  |  |  | 9046
Activity | A02-03 | Assessment of CD needs | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 10000 | 3000 | 3000 | 4000 | 3000 | 3000 | 4000 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8300 | 8700 | 3000 | 3000 | 4000 | 0 | 5000 | 5000 | 3264 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Updated | [11 empty] | 0 | 4000 | 4000 | 0 | 0 | 3424 | 3424 | 0 | 0 | 3000 | 3000 | 4000 | 0 | 0 | 12656 | 0 | 0 | 3729 | 0 | 0 |  | 0 | 0
Activity | A02-04 | Strengthen the MPI's current system of support to individual CD | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7000 | 8000 | 5000 | 0 | 5000 | 0 | 10000 | 10000 | 10000 | 10000 |  | 5000 | 5000 | 10000 | 5000 | 1250 | 5000 | 5000 | 1250 | 5000 |  | 5000 | 0 | 4201
|  |  | Updated | [8 empty] | 0 | 0 | 6418 | 10000 | 10000 | 10000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 16766 | 5000 | 5000 | 0 |  | 3313 | 0 |  |  | 0 | 6969 | 0 | 10000 | 10000 | 11435 | 2000 |  | 5669 | [5 empty] | 3795 | 4201
Activity | A02-05 | Create core group of skilled planners in MPI | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 20000 | 3000 | 3000 | 4000 | 3000 | 3000 | 4000 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 2400 | 12500 |  |  |  |  | 12500 | 12500 |  |  | 4000 | 4000 | 4500 |  |  | 13500 |  |  | 13500 |  | 5000 | 5000
|  |  | Updated | [9 empty] | 0 |  | 5000 | 5000 | 0 | 3000 | 3000 | 4000 | 10000 | 0 | 0 | 3000 | 3000 | 4000 | 0 | 24936 | 10000 | 0 |  |  | 0 |  |  | 0 |  |  | 10000 | 10000 | 11014 |  |  | 0 |  |  | 12646 |  | 5000 | 5566
Result 3 |  | Increased capacity of provincial authorities and 2-3 line Ministries to adopt improved planning
Activity | A03-01 | Draft technical guidelines & Manuals | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 11500 | 11500 | 11500 | 11500 | 11500 | 11500 | 11500 | 11500 | 11500 | 11500 | 12500 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 5434 | 5000 | 5000 | 10000 | 5000 | 5000 | 10348 |  | 5000 | 5000
|  |  | Updated | [8 empty] | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 3000 | 0 | 0 | 14500 | 4000 | 4750 | 0 | 11626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4432 | 0 | 0 |  |  |  | 0 | 0 | 9853 |  |  | 3405 |  | 10000 | 10561
Activity | A03-02 | Basic training to Sub-national staff | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 |  | 10000 | 10000 |  | 11367 |  | 36929 | 0 | 30000 | 30000 | 25882 |  |  |  | 110000 | 80000
|  |  | Updated | [9 empty] | 17197 | 10000 | 10000 | 10000 | 10000 | 20000 | 0 | 10000 | 22311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 80000 | 80000 | 83718 |  | 36929 |  | 30000 | 30000 | 23226
Activity | A03-03 | Embedded Capacity Building in 5 provinces | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 4000 | 3000 | 3000 | 4000 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 7400 | 5000 | 0 | 5000 | 5000 | 0 | 50000 | 50000 | 0 | 5000 | 5000 | 0 | 5000 |  |  | 0 | 34632 |  |  |  | 1476
|  |  | Updated | [11 empty] | 0 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 20000 | 0 | 0 | 60000 | 1000 | 1000 | 1880 |  |  |  | 50000 | 50000 | 68193 |  | 5000 | 5970 |  |  |  | 8758 |  |  |  | 1276
Activity | A03-04 | Support to Regional Integration Mechanism | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
|  |  | Updated | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 20000
Activity | A03-05 | Basic training of key Ministries staff | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 2750 | 2750 | 2750 | 2750 | 2750 | 2750 | 2750 | 2750 | 2750 | 2750 | 2750 | 0 | 0 | 0 | 0 | 0 | 2133 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2133
|  |  | Updated | [8 empty] | 0 | 9745 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 10000 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 13339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity | A03-06 | Core skilled planners/facilitators | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 2900 | 3100 | 0 | 0 | 0 | 0 | 0 | 5000 | 4237 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 9237
|  |  | Updated | [11 empty] | 0 | 10000 | 10000 | 0 | 0 | 0 | 2000 | 5000 | 4500 | 1000 | 2750 | 2000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity | A03-07 | Develop CB strategies in selected Ministries | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 6600 | 7400 | 0 | 0 | 3588 | 5000 | 5000 | 10000 | 10000 | 5000 | 5000 | 0 | 5000 | 5000 | 10000 | 10000 | 30000 | 10000
|  |  | Updated | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5091 | 0 | 0 | 16670
Result 4 |  | Increased capacity of selected local authorities to adopt improved planning and M&E systems
Activity | A04-01 | CD strategy for improved planning in one district | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 10500 | 11500 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 0 | 0 | 20000 | 20000 | 31500 | 50000 | 100000 | 100000 | 50000 |  |  |  | 40000 | 45000 | 2500 | 2500 | 2423
|  |  | Updated | [11 empty] | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3640 | 50000 | 50319 | 100000 | 50000 | 90000 | 91095 |  | 40000 | 59169 | 1200 | 1200 | 1164
Activity | A04-02 | Support integration of SED and SDF | Planned | 2014-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Updated

## Audit Action Plan
Open
PROJECT CODE |  |  | VIE1204811 | [11 empty] | Closed | CdC (Court of Auditors) | Public Procurements
PROJECT NAME |  |  | Capacity Development for Planning Reform | [11 empty] | Ongoing | CdC/BST | Agreements
REFERENCE YEAR |  |  | 2017 | [11 empty] | Abandonned | CdC/BDO | Procurement cycle
REFERNCE QUARTER |  |  | Q2 | [12 empty] | CdC/CdP | HR
[16 empty] | CdC/CdP/BST | Accounting
Identification observation/recommandation | [7 empty] | Plan action |  |  | Suivi |  |  |  |  | BST | VAT
Code Navision | Year | Audit report ref | Audit firm | if other: firm name | Observation | Recommendation | Recommendation's domain | Actions | Responsible | Deadline | Achieved | Still to implement/ comments | Status | New deadline |  | BDO | Adminsitration (filing/archiving)
VIE1204811 | 2015 | Audit report - September 2015 | CdC/CdP/BST |  | Booking of all the BTC financial contributions on a single budget line and as a result, budget overruns over two lines (A_01_01, A_04_01) and on the other hand, no disbursment on the other lines | to split the financial contribution between the lines were the expenses are done (according to the financial report prepared quarterly by the project) | Accountancy |  | BTC | [6 empty] | MS | Logistics (assets / fuel / …)
VIE1204811 | 2015 | Audit report - September 2015 | CdC/CdP/BST |  | no assets inventory with the mention of localization for all of them | to establish a fixed assets inventory with the mention of the localization for all of them | Logistics (assets / fuel / …) | Will establish the FA inventory with the mention of localization | PMU | 31/12/2015 | [6 empty] | Rules/ Procedures
VIE1204811 | 2015 | Audit report - September 2015 | CdC/CdP/BST |  | Car expenses: for the moment only the km per trip without any mention of sum/total. | to mention the km at the beginning and at the end of the trip (to ensure the completeness) | Logistics (assets / fuel / …) | Mention km at the beginning and end of the trip | PMU | 1/10/2015- | [6 empty] | Project Cycle (start/end)
VIE1204811 | 2015 | Audit report - September 2015 | CdC/CdP/BST |  | A procedure of « shopping / competitive bidding » is used to book the housing and catering of the workshops. Those workshops are recurring and their cumulative value is higher than the threshold allowing the use of that procedure | The project should investigate the feasibility of a framework contract which could also result into a saving of costs. | Tendering / Procurement | [8 empty] | El Wafa
VIE1204811 | 2015 | Audit report - September 2015 | CdC/CdP/BST |  | The project is asking for quotations on the phone, without any written invitation. This doesn’t comply with the regulation nor with the principles of transparency and fair competition. | To make use of email instead of phone to ensure transparency and fair competition. | Tendering / Procurement | For the threshold required in TFF, from October 2015, their quotations have been asked by written invitation | PMU | 1/10/2015-
VIE1204811 | 2015 | Audit report - September 2015 | CdC/CdP/BST |  | The technical specifications of a tender (purchase of IT equipment) are based on a specific model. Even though equivalents might be accepted , the competition is too restricted | Limit the specfications to the ones that are meaningful. Make use of minimum/maximum and/or brackets for the requirements | Tendering / Procurement | Will try to avoid precise specific model in the technical specification, especially in IT equipment | PMU | 1/10/2015-
VIE1204811 | 2015 | BXL1291-005-2015 | E&Y |  | 1, in workshops “Popularizing Law on Public Investment" taking place on 6-7, 7-8, 8-9 August 2014 respectively in Danang, some delegates neither signed on the attendance list nor meal and transportation allowance list, but were signed on behalf by other delegates; | 1, The Project Management should adopt measures to communicate the policy on sign-off to acknowledge the receipt of allowances for attendees at conferences, ensuring the validity of disbursement supporting documents and the transparency of disbursements in general; | Rules/ Procedures | Informed participants on policy on sign-off in receiving allowances in workshops | PMU | 2014-09-01
VIE1204811 | 2015 | BXL1291-005-2015 | E&Y |  | the procurement of goods and service amounting from EUR 8,501 to EUR 85,000 is required to follow competitive negotiated procedure with at least three (03) invitations to bidders, setting detailed specifications and sample quotation. In fact, the Project simply requests quotations from bidders by phone without sending written invitations to bidders. This adversely affects the compliance with regulation and policies of the Project as well as the transparency and fair competition of the procurement. This may lead to the risk that the Project fails to select the best qualified and competitive bidder. | strictly comply with public procurement procedure specified by TFF to ensure the transparency and fair competition of the procurement as well as the economic efficiency of the Project. | Public Procurements | For the threshold required in TFF, from October 2015, their quotations have been asked by written invitation | PMU | 2015-10-01
VIE1204811 | 2016 | Audit 2016 | CdC/CdP/BST |  | The cash book is held under an excel file, which is compliant to Vnese regulation | BTC procedures require the cash book be held in written as a good pratice of internal control | Rules/ Procedures | The project has used the cashbook written | PMU
VIE1204811 | 2016 | Audit 2016 | CdC/CdP/BST |  | Procurement: The launch of the W/S and trainings (TEUR170 from 1/2016 to 8/2016) is done at a very short notice (3 to 7 days). This has an impact on the price and the availability of hosting facilities. This may also affect the participation of the target public. | to improve the planning of those workshops and training | Public Procurements
VIE1204811 | 2016 | Audit 2016 | CdC/CdP/BST |  | When it is decided to organise a workshop or training, the project looks for a hotel that is suitable and available. He then asks three agencies for a quotation for that particular hotel. | The correct process is to ask at least three agencies for a quotation with a request for the specific needs (number of rooms, catering, conference room, facilities, etc.) and let the agencies come with their best proposal | Public Procurements | [9 empty] | Irregularity
VIE1204811 | 2016 | Audit 2016 | CdC/CdP/BST |  | Some budget lines are already exceed. As a consequence, a budget modification procedure has been started in July and requires BTC's agreement. Said agreement will depend on the mid-term review conclusions which is currently ongoing | [5 empty] | All budget modifications have to be approved by PSC. The Project never exceed the budget lines approved.
VIE1204811 | 2016 | Audit 2016 | E&Y |  | In each workshop, there are only 2 lists of participants have been signed | Participants have to signed in each and everyday of the workshop. |  |  |  |  | 2 lists of participants signed in order to saving time for participants. We still control the number of participants attended in each workshop day. Those did not register the first day and attend the last day can not receive the allowances.
Note on D2: CTB: * Link to do with first sheet of MONOP/MOPA * put as sheet "yellow" after MSE
Note on A8: CTB: For Representation: code REP, for Headquater: code HQ
Note on C8: CTB: Mention the audit report reference linked to the observation Either the order form reference for project's audit (eg: BXL1291-BDI 001-2014) or the title of the audit report for the other types of audits (eg: REP & Projets RWA Août 2013)
Note on D8: CTB: Which firm has drafted the report?
Note on E8: CTB: If the firm is different from BTC's external control bodies or the framework contract. Empty field. Select "Other" in the audit firm column and precise the firm's name.
Note on J8: CTB: Fill in a function not a name.
Note on N8: CTB: - Open: no action taken. - Ongoing: partially implemented, comment the actions still open in the previous field and mention a new deadline if necessary for those actions. - Closed: corrective action fully implemented. - Abandoned: In case of abandonment, the reasons have to be explained as well as the way that the risks are taken into account and reduced to an acceptable level. To mention in the previous field (still to implement/comments)
Note on A9: CTB: Pour la représentation mettre le code REP, pour le siège le code HQ
Note on A10: CTB: Pour la représentation mettre le code REP, pour le siège le code HQ
Note on C10: CTB: Soit le numéro du bon de commande pour les audits projets (ex: BXL1291-BDI 001-2014) ou le titre du rapport pour les autres audits (ex: REP & Projets RWA Août 2013)
Note on A11: CTB: Pour la représentation mettre le code REP, pour le siège le code HQ
Note on C11: CTB: Soit le numéro du bon de commande pour les audits projets (ex: BXL1291-BDI 001-2014) ou le titre du rapport pour les autres audits (ex: REP & Projets RWA Août 2013)
Note on A12: CTB: Pour la représentation mettre le code REP, pour le siège le code HQ
Note on C12: CTB: Soit le numéro du bon de commande pour les audits projets (ex: BXL1291-BDI 001-2014) ou le titre du rapport pour les autres audits (ex: REP & Projets RWA Août 2013)
Note on A13: CTB: Pour la représentation mettre le code REP, pour le siège le code HQ
Note on C13: CTB: Soit le numéro du bon de commande pour les audits projets (ex: BXL1291-BDI 001-2014) ou le titre du rapport pour les autres audits (ex: REP & Projets RWA Août 2013)
Note on A14: CTB: Pour la représentation mettre le code REP, pour le siège le code HQ
Note on C14: CTB: Soit le numéro du bon de commande pour les audits projets (ex: BXL1291-BDI 001-2014) ou le titre du rapport pour les autres audits (ex: REP & Projets RWA Août 2013)
Note on A15: CTB: Pour la représentation mettre le code REP, pour le siège le code HQ
Note on A16: CTB: Pour la représentation mettre le code REP, pour le siège le code HQ
Note on A21: CTB: Pour la représentation mettre le code REP, pour le siège le code HQ