# FINAL REPORT

ACTIVITES DE REHABILITATION DANS LES SECTEURS DE L’EAU ET DE L’ELECTRICITE

19410/51 PZA/02/008/11

BASIC INFORMATION ON THE PROJECT

Country					: PALESTINIAN TERRITORIES

DAC Sector and subsector			: Infrastructure

National or regional institution in charge of the execution: Palestinian Water Authority & Palestinian Electricity Authority

Agencies in charge of the execution 		: BTC

Number of BTC international cooperation experts: 0

Duration of the project (according to SA/SC)	: 18 months

Start date of the project:

according to CMO	:  12 January 2004

effective 		:  12 January 2004

End date of the project:

according to CMO	: 12 july 2005

effective		: october 2005

Project management methods			: Regie

Total budget for the project			: 878.000 €

Period covered by the report:			: January 2004 to 0ctober 2005

| Annexes | Yes | No |
| --- | --- | --- |
| Results summary | X |  |
| Situation of receipts and expenses for the year considered | X |  |
| Disbursement rate of the project | X |  |
| Personnel of the project | X |  |
| Subcontracting activities and invitations to tender | X |  |
| Equipments | X |  |
| Trainings | X |  |
| Backers |  |  |

PART ONE : APPRAISAL

Evaluate the relevance and the performance of the project by means of the following assessments:

1. - Very satisfactory 
2. - Satisfactory

3. - Non satisfactory, in spite of some positive elements 
4. - Non satisfactory
X. - Unfounded

Write down your answer in the column corresponding to your functions during the project execution.:

|  | National execution official | BTC execution official |
| --- | --- | --- |
| RELEVANCE (cf. PRIMA, §70, p.19) |  |  |
| 1. Is the project relevant compared to the national development priorities? | 1 | 1 |
| 2. Is the project relevant compared to the Belgian development policy? Indicate your result according to the three themes below: Gender Environment Social economy | X 1 1 | X 1 1 |
| 3. Were the objectives of the project always relevant? | 1 | 1 |
| 4. Did the project meet the needs of the target groups? | 1 | 1 |
| 5. According to its objectives, did the project rely on the appropriate local execution organs? | 1 | 1 |

|  | National execution official | BTC execution official |
| --- | --- | --- |
| RELEVANCE (PRIMA, §71, pp.19-20) |  |  |
| Did the results of the project contribute to the carrying out of its objectives ? (efficiency) | 1 | 1 |
| Evaluate the intermediate results (efficiency) | 1 | 1 |
| Are the management methods of the project appropriated? (efficiency) | 1 | 1 |
| Were the following resources appropriated (efficiency) : | 1 | 1 |
| a. Financial means? | 1 | 1 |
| b. Human resources ? | 1 | 1 |
| c. Material and equipments? | 1 | 1 |
| Were the project resources effectively used and optimized in order to reach the foreseen results? (efficiency) | 1 | 1 |
| Was the project satisfactory on a cost-efficiency approach in comparison to similar interventions? (efficiency) | 1 | 1 |
| According to the execution planning, assess the speed of the execution. (respect of deadlines) | 2 | 2 |

Indicate your global evaluation of the project by means of the following appreciations:

1 - Very satisfactory
2 - Satisfactory
3 - Non satisfactory, in spite of some positive elements 
4 - Non satisfactory
X - Unfounded

|  | National execution official | BTC execution official |
| --- | --- | --- |
| Global evaluation of the project | 1 | 1 |

Comment your evaluation, which can be broader than the strict framework of the abovementioned relevance and performance criteria and differ from the given evaluation.

Essentially all the needed equipment has been provided with the aim of improving the living conditions of the Palestinian population through the creation of job opportunities and the rehabilitation of infrastructure.

The tender procedure has been longer that initially anticipated.

For the PEA the supply was done after the end date of the contract with partial acceptable justifications from the contractor.

PWA the supplies were delivered before the end date of the contract.

| National execution official | BTC execution official |
| --- | --- |

PART TWO : SUMMARY OF THE PROJECT IMPLEMENTATION.

- If necessary, describe the Specific objectives and the Intermediate results of the project, as mentioned in the project document, as well as the implemented changes (when, how and why).

Specific Objective:	Improvement of the poor living conditions of the Palestinians in the West Bank affected by the damages created by the Israeli invasion.

Intermediate Result 1:	Transformers for electricity distribution are available in the PEA storage area in the West Bank for the damages repairs of the affected municipalities.

Intermediate Result 2:	Pipes and water equipment for water distribution network are available in the PWA storage area in the West Bank for the damages repairs of the affected municipalities.

There were no changes in the implementation.

- To which extent was the specific objective of the project reached, according to the accepted indicators?

The specific objective was reached according to the indicators:  Transformers for electricity and pipes and water equipment are delivered to the PEA and PWA storage respectively.

- To which extent were the intermediate results of the project reached, according to the accepted indicators?

The final quantities of electricity equipment (transformers) to be ordered was according to the final unit rates received from the suppliers after the tender procedure.  In addition, the final quantities for water equipment to be ordered was according to the final unit rates received from the suppliers after the tender procedure.  Both tenders electricity equipment and water equipment were including the BTC rights to vary quantities at time of award. Tender documents were launched and awarded , equipments are delivered to the storage areas and reception of the equipments were done.

- Describe the follow-up evaluation system established when the project was implemented.

BTC was completely following up the tender documents, tender procedure, awarding contracts, the manufacturing aspect and the transport to the storage areas, and the handing over of the imported goods.

Several visits were conducted by the Resident Representative and the Technical Assistant to the storage areas to inspect and check the delivered equipment.

PART THREE : COMMENTS AND ANALYSIS.

- What are the major problems and questions having influenced the project implementation and how did the project attempt to solve them?

No major problems having influenced the project implementation except for delays in tenders procedures.

- Which factors explain the differences in relation to the awaited results?

No major factors having differences in relation to the awaited results.

- Which lessons can we learn from the project experience? Please give a detailed answer on the impact and the durability of the results.

  - Budget evaluation during the formulation to be improved

  - Fluctuation of the exchange rates of the EURO

  - Time to obtain the tax exemption with goods held in the airport

- According to you, how was the project perceived by the target groups?

Highly positive.

- Did the follow-up evaluation or the monitoring, and the possible audits and controls have any results? How were the recommendations taken into account?

NO

- Which are your recommendations for the consolidation and the appropriation of post-project period ( policy to be followed or implemented, necessary national resources, make target groups aware of their responsibilities, way to apply the recommendations …)?

No Specific Recommendations.

7. Conclusions

The donated equipment by Belgium government to the PEA and PWA was highly appreciated since the need to purchase new equipment for the ICU was one of its priorities.  The Belgium investment dealt with emergency issues in the Electricity and Water Sectors arising from March – April campaign in the West Bank.  For since the start of the present Intifada “end of August 2000” and till today, there have been many incursions by the Israeli army into the Palestinian Territories, both in Gaza and West Bank.  This has resulted in considerable damages to the Palestinian water and electricity sector.  Such damages have occurred throughout the Intifada, but the Israeli incursions in the West Bank in March-April 2002 resulted in particularly severe damages to the infrastructure.

It is clear that replenishing of stocks to a reasonable level was absolutely essential to maintain the ability of the electricity and waters sectors to handle emergencies.

The stocks of water and electrical equipments are now available in the West Bank storage facilities managed by the PWA and PEA. The Belgian donated spare parts are part of donors contribution for replenishment of equipment to cover the needs of municipalities and villages.

No specific agreement was signed between the Belgian Government and the Palestinian National Authority.  A Memorandum of Understanding was signed between BTC, PWA and PEA for the implementation of this rehabilitation project based on the formulation document and designed budget.

| National execution official | BTC execution official |
| --- | --- |

ANNEX 1. Results and activities summary (according to the logical framework)

| Intermediate results | Indicators (foreseen or realized) | Progress |
| --- | --- | --- |
| IR. 1. | Transformers for electricity distribution network are available in the PEA storage area in the West Bank for the damages repairs of the affected municipalities | Finalised |
| IR. 2. | Pipes and water equipment for water distribution network are available in the PWA storage area in the West Bank for the damages repairs of the affected municipalities | Finalised |
| Planned activities | Progress of the activities (with comments and remarks) |

| IR.1. Transformers PEA Activity 1: Signature of the "convention de mise en oeuvre3 Activity 2: Notification of the transfer of 80% funds from the DGCD Activity 3: Publication in the newspapers of the appeal for candidates Activity 4: Reception of the candidates files Activity 5: Starting of a negotiated procedure by expedition of the updated tender file. Activity 6: Reception of the tenders Activity 7: Awarding of the Contract Activity 8: Provisionally acceptance of the goods in suppliers warehouse (Spain) Activity 9: Provisory acceptance in PEA storage area (West Bank) | May 2003 January 2004 March 2004 April 2004 but no candidates files received August 2004 October 2004 January 2005 June 2005 August 2005 |
| --- | --- |

| IR.2. Pipes and water equipment PWA Activity 1: Signature of the "convention de mise en oeuvre3 Activity 2: Notification of the transfer of 80% funds from the DGCD Activity 3: Publication in the newspapers of the appeal for candidates Activity 4: Reception of the candidates files Activity 5: Starting of a negotiated procedure by expedition of the updated tender file. Activity 6: Reception of the tenders Activity 7: Awarding of the Contract Activity 8: Provisionally acceptance of the goods in suppliers warehouse (France) Activity 9: Provisory acceptance in PWA storage area (West Bank) | May 2003 January 2004 March 2004 April 2004 but no candidates files received June 2004 July 2004 September 2005 January 2006 April 2005 |
| --- | --- |

ANNEX 2 :	Expenses and disbursement rate

| Item | Description | Finance Mode | Budget Amount | Expenses | Balance | Exec rate |
| --- | --- | --- | --- | --- | --- | --- |
| A | Emergency assistance |  |  |  |  |  |
| 01 | Supply of Water Equipment to Storage in West Bank | Regie | 439,000.00 | 438,625.07 | 374.93 | 99,9% |
| 02 | Spare part Electricity Equipment to final Storage Area in West Bank | Regie | 439,000.00 | 428,273.43 | 10.725,57 | 97,5% |
|  | TOTAL |  | 878,000.00 | 866,.896.50 | 11,101.50 | 99% |

*The difference between the amount of the contract awarding (see annex 5) and the real expenses are due to penalties for late completion.

ANNEX 4	: Personnel of the project

| Personnel type (title, name and gender) | Duration of recruitment (start and end dates) | Comments ( recruitment periods, profile relevance …) |
| --- | --- | --- |
| National personnel put at disposal by the Partner Country | PEA: Eng. Naif A. Halim, General Project Director PEA Eng. Mohannad Aqel, Director PEA |  |
| Support personnel, locally recruited | PWA: Eng. Mohammad Jaas, General Director of West Bank Water Department Eng. Nael Ali Ahmad, Engineer West Bank Water Department |  |
| Training personnel, locally recruited | NA |  |
| International Personnel (outside BTC) | NA |  |
| Expert in International Cooperation (BTC) Mr. Van Vaerenbergh, BTC TA | Part time | Preparation of the tender document, tender evaluation, reception report |

ANNEX 5: Subcontracting activities and invitations to tender

PEA TRANSFORMERS

Tendering mode				: Negotiated procedure without publicity

Date of the invitation to tender			: August 2004

Start date of the subcontracting contract		: 13 January 2005

Name of the subcontractor (or of the company)	: Satco

Object of the contract				: Supply Transformers

Cost of the contract				: 435,988 EURO

Duration of the contract				: Thirteen weeks

Results :		Very satisfactory but delays in the time of completion of the contract

Comments :	The supply was done after the end date of the contract with partial acceptable justifications from the supplier

PWA WATERPIPES AND ACCESSORIES

Tendering mode				: Negotiated procedure without publicity

Date of the invitation to tender			: June 2004

Start date of the subcontracting contract		: 15 September 2004

Name of the subcontractor (or of the company)	: IPS

Object of the contract				: Supply of water pipes and accessories

Cost of the contract				: 437,725.97 EURO

Duration of the contract				: 150 Days

Results :		Very satisfactory

Comments :	The supply was done before the end date of the contract

ANNEX 6	: List of the equipments acquired during the project

Transformers PEA

| Revised BOQ |
| --- |
| Item No. | Description | Unit | Quantity | Unit Price CIP " Tulkarem " | Total Price CIP" Tulkarem" |
|  |  |  |  | Euro | Euro |
| 1 | Transformer 11/.4 kV 400 KVA | Unit | 11 | 4991 | 54901 |
| 2 | Transformer 11/.4 kV 630KVA | Unit | 12 | 5187 | 62244 |
| 3 | Transformer 11/.4 kV 250 KVA | Unit | 4 | 3674 | 14696 |
| 4 | Transformer 11/.4 kV 160 KVA | Unit | 4 | 3175 | 12700 |
| 5 | Transformer 22/.4 kV 250KVA | Unit | 6 | 3749 | 22494 |
| 6 | Transformer 22/.4 kV 400 KVA | Unit | 14 | 5094 | 71316 |
| 7 | Transformer 33/.4 kV 160 KVA | Unit | 1 | 2863 | 2863 |
| 8 | Transformer 33/.4 kV 250 KVA | Unit | 3 | 3312 | 9936 |
| 9 | Transformer 33/.4 kV 400 KVA | Unit | 14 | 4117 | 57638 |
| 10 | Transformer 33/.4 kV 630 KVA | Unit | 25 | 5088 | 127200 |
| Total |  | 435988 |

Water pipes PWA

| Item No. | Description | Unit | Qty. | Unit Price CIP " Ramallah " |  | Total Price CIP " Ramallah" |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Euro | C | Euro | C |
| 1 | Standard Socket ( Push in Joint), Centrifugally cast (class- k9) ductile iron pipe,, 60 mm DN(2"), with the required sealing gaskets, lined from inside with cement mortar , and coated from outside with a layer of metallic zinc (minimum quantity 200 glm2) | L.M | 7.280 | 13,80 | 100.464,00 |
| 2 | Standard Socket ( Push in Joint), Centrifugally cast (class- k9) ductile iron pipe, 80 mm DN (3"), with the required sealing gaskets, lined from inside with cement mortar , and coated from outside with a layer of metallic zinc (minimum quantity 200 glm2 a | L.M | 5.005 | 14,59 | 73.022,95 |
| 3 | Standard socket ( push in joint ) centrifugally cast class- k9 ductile iron pipe, 100 mm DN(4"), with the required sealing gaskets, lined from inside with cement mortar, and coated from outside with a layer of metallic zinc (minimum quantity 200 glm2 and | L.M | 4.277 | 16,06 | 68.688,62 |
| 4 | Standard socket ( push in joint ) centrifugally cast class- k9 ductile iron pipe, 60 mm DN(2"), with self anchthed restrained joints, including a WELD bead, sealing gaskets, locking rings, glands and bolts - pipes are lined from inside with cement mortar | L.M | 1.350 | 14,26 | 19.251,00 |
| 5 | Standard socket (push in joint) centrifugally cast class- k9 ductile iron pipe,80 mm DN(3"), with self anchthed restrained joints, including a weld bead, sealing gaskets, locking rings, glands and bolts - pipes are lined from inside with cement mortar and | L.M | 900 | 18,95 | 17.055,00 |
| 6 | Standard socket ( push in joint ) centrifugally cast class- k9 ductile iron pipe, 100 mm DN(4"), with self anchthed restrained joints, including a weld bead, sealing gaskets, locking rings, glands and bolts - pipes are lined from inside with cement mortar | L.M | 825 | 21,29 | 17.564,25 |
| 7 | Double socket ductile iron Tee, DN 60× 60 mm (2"), with 60 mm rota table flanged branch for PN 16 bars with the required sealing gaskets bolts & nuts, coated from inside & outside with epoxy powder, minimum thickness 200 micron This shall be applied for a | Piece | 23 | 66,04 | 1.518,92 |
| 8 | Double socket ductile iron Tee, DN 80× 80 mm (3"), with 80 mm rota table flanged branch for PN 16 bars with the required sealing gaskets bolts & nuts coated from inside & outside with epoxy powder, minimum thickness 200 micron | Piece | 18 | 74,04 | 1.332,72 |
| 9 | Double socket ductile iron Tee, DN 80× 80 mm (3"), with 60 mm (2") rota table flanged branch for PN 16 bars with the required sealing gaskets bolts & nuts, coated from inside & outside with epoxy powder, minimum thickness 200 micron | Piece | 18 | 59,44 | 1.069,92 |
| 10 | Double socket ductile iron Tee, DN 100× 100 mm (4"), with 100 mm (4")rota table flanged branch for PN 16 bars with the required sealing gaskets bolts & nuts coated from inside & outside with epoxy powder, minimum thickness 200 micron | Piece | 9 | 94,25 | 848,25 |
| 11 | Double socket ductile iron Tee, DN 100× 100 mm (4"), with 80 mm (3") rota table flanged branch for PN 16 bars with the required sealing gaskets bolts & nuts, coated from inside & outside with epoxy powder, minimum thickness 200 micron | Piece | 18 | 79,45 | 1.430,10 |
| 12 | Double socket ductile iron Tec, DN 100× 100 mm (4"), with 60 mm (2") rota table flanged branch for PN 16 bars with the required sealing gaskets bolts & nuts, coated from inside & outside with epoxy powder, minimum thickness 200 micron | Piece | 18 | 88,36 | 1.590,48 |
| 13 | 90 Degree double socket bend, DN 60 mm (2") including the required gaskets. | Piece | 32 | 52,13 | 1.668,16 |
| 14 | 45 Degree double socket bend, DN 60 mm (2") including the required gaskets. | Piece | 41 | 36,62 | 1.501,42 |
| 15 | 22-1/2 Degree double socket bends, DN 60 mm (2") including the required gaskets. | Piece | 46 | 32,52 | 1.495,92 |
| 16 | 11-1/4 Degree double socket bends, DN 60 mm (2") including the required gaskets. | Piece | 46 | 33,54 | 1.542,84 |
| 17 | 90 Degree double socket bend, DN 80 mm (3") including the required gaskets. | Piece | 27 | 57,13 | 1.542,51 |
| 18 | 45 Degree double socket bend, DN 80 mm (3") including the required gaskets. | Piece | 36 | 41,23 | 1.484,28 |
| 19 | 22-1/2 Degree double socket bends, DN 80 mm (3") including the required gaskets. | Piece | 36 | 48,09 | 1.731,24 |
| 20 | 11-1/4 Degree double socket bends, DN 80 mm (3") including the required gaskets. | Piece | 36 | 40,12 | 1.444,32 |
| 21 | 90 Degree double socket bend, DN 100 mm (4") including the required gaskets . | Piece | 27 | 58,46 | 1.578,42 |
| 22 | 45 Degree double socket bend, DN 100 mm (4") including the required gaskets . | Piece | 32 | 49,81 | 1.593,92 |
| 23 | 22-1/2 Degree double socket bends, DN 100 mm (4") including the required gaskets. | Piece | 36 | 45,42 | 1.635,12 |
| 24 | 11-1/4 Degree double socket bend, DN 100 mm (4") including the required gaskets. | Piece | 36 | 46,90 | 1.688,40 |
| 25 | Double flanged gate valve, DN 50 mm (2"). short length- PN 16 bars, coated with epoxy powder minimum thickness 200 micron, complete with the two companion flanges, metal reinforced gaskets, bolts, nuts and hand wheel | Piece | 32 | 141,93 | 4.541,76 |
| 26 | Double flanged gate valve, DN 80 mm(3")-short length- PN 16 bars, coated with epoxy powder minimum thickness 200 micron, complete with the two companion flanges, metal reinforced gaskets, bolts, nuts and hand wheel | Piece | 21 | 171,26 | 3.596,46 |
| 27 | Double flanged gate valve, DN 100 mm(4")- short length- PN 16 bars, coated with epoxy powder minimum thickness 200 micron, complete with the two companion flanges, metal reinforced gaskets, bolts, nuts and hand wheel | Piece | 18 | 197,08 | 3.547,44 |
| 28 | Double orifice air valve, flanged type , DN 50 mm(2") PN 16 bars, coated with epoxy powder minimum thickness 200 micron, with and metal reinforced gaskets, bolts nuts | Piece | 9 | 312,25 | 2.810,25 |
| 29 | Double socket taper reducer 80-60mm(from 3" to 2") with the required gaskets | Piece | 13 | 37,54 | 488,02 |
| 30 | Double socket taper reducer 100-80mm(from 4" to 3") with the required gaskets | Piece | 9 | 45,76 | 411,84 |
| 31 | Double socket taper reducer 100-60mm(from 4" to 2") with the required gaskets | Piece | 9 | 44,03 | 396,27 |
| 32 | Connecting piece adaptor to connect ductile iron pipe, DN 60 mm(2") from one side, and steel pipe maximum and minimum outside diameter (60.8, and 59.7 respectively) mm(2") from the other side | Piece | 46 | 101,24 | 4.657,04 |
| 33 | Connecting piece adaptor to connect ductile iron pipe, DN 80 mm(3") from one side, and steel pipe maximum outside diameter 88.9 mm(3") from the other side | Piece | 36 | 33,45 | 1.204,20 |
| 34 | Connecting piece adaptor to connect ductile iron pipe, DN 100 mm(4") from one side, and steel pipe maximum outside diameter 114.3 mm(4") from the other side | Piece | 32 | 39,08 | 1.250,56 |
| 35 | Wide adjustment, self- restrained dismantling joint, DN 60mm(2") PN 16 bars | Piece | 36 | 136,67 | 4.920,12 |
| 36 | Wide adjustment, self- restrained dismantling joint, DN 80mm(3") PN 16 bars | Piece | 23 | 162,53 | 3.738,19 |
| 37 | Wide adjustment, self- restrained dismantling joint, DN 100mm(4") PN 16 bars | Piece | 23 | 175,82 | 4.043,86 |
| 38 | Repair piece (coupling or similar) of Ductile iron pipe, DN 60mm (2") | Piece | 13 | 46,79 | 608,27 |
| 39 | Repair piece (coupling or similar) of Ductile iron pipe, DN 80mm (3") | Piece | 9 | 52,78 | 475,02 |
| 40 | Repair piece (coupling or similar of Ductile iron pipe, DN 100mm (4") | Piece | 9 | 57,47 | 517,23 |
| 41 | Double rota table flange (PN 16 bars ) anchoring ductile iron pipe piece, DN 60 mm(2") with welded puddle flange in the middle, L= 1000mm including two metal reinforced gaskets for each piece | Piece | 34 | 77,67 | 2.640,78 |
| 42 | Double rota table flange (PN 16 bars ) anchoring ductile iron pipe piece, DN80 mm(3") with welded puddle flange in the middle, L= 1000mm including two metal reinforced gaskets for each piece | Piece | 23 | 87,92 | 2.022,16 |
| 43 | Double rota table flange (PN 16 bars ) anchoring ductile iron pipe piece, DN 100 mm(4") with welded puddle flange in the middle, L= 1000mm including two metal reinforced gaskets for each piece | Piece | 23 | 113,36 | 2.607,28 |
| 44 | Rota table flange -spigot anchoring ductile iron pipe piece, DN 60mm (2"),PN 16 bars with welded puddle flange in the middle, L= 1000 mm including metal reinforced gasket | Piece | 34 | 77,67 | 2.640,78 |
| 45 | Rota table flange -spigot anchoring ductile iron pipe piece, DN 80mm (3"),PN 16 bars with welded puddle flange in the middle, L= 1000 mm including metal reinforced gasket | Piece | 23 | 87,88 | 2.021,24 |
| 46 | Rota table flange- Spigot anchoring ductile iron pipe piece, DN 100 mm (4") , PN 16 bars, with welded puddle flange in the middle, L = 1000mm, including metal reinforced gasket | Piece | 23 | 113,36 | 2.607,28 |
| 47 | Ductile iron flanged - socket - piece (adaptor), DN 60 mm (2) " , PN 16, including metal reinforced gasket, bolts and nuts for the flange, and needed gasket for socket | Piece | 57 | 53,41 | 3.044,37 |
| 48 | Ductile iron flanged - socket - piece (adaptor), DN 80 mm (3) " , PN 16, including metal reinforced gasket, bolts and nuts for the flange, and needed gasket for socket | Piece | 23 | 62,68 | 1.441,64 |
| 49 | Ductile iron flanged - socket - piece (adaptor, DN 100 mm (4) " , PN 16, including metal reinforced gasket, bolts and nuts for the flange, and needed gasket for socket | Piece | 36 | 64,23 | 2.312,28 |
| 50 | Ductile iron blank flange DN 60 mm (2") , PN 16 | Piece | 23 | 10,76 | 247,48 |
| 51 | Ductile iron blank flange DN 80 mm (3") , PN 16 | Piece | 18 | 14,33 | 257,94 |
| 52 | Ductile iron blank flange DN 100 mm (4"),PN 16 | Piece | 13 | 16,66 | 216,58 |
| 53 | Complete wide range tapping saddle, DN 60 mm(2") with DN 20 mm( 3/4") threaded outlet, including the gasket, bolts & nuts | Piece | 478 | 23,98 | 11.462,44 |
| 54 | Complete wide range tapping saddle, DN 60 mm(2") with DN 25 mm (1") threaded outlet including gaskets bolts and nuts | Piece | 78 | 23,98 | 1.870,44 |
| 55 | Complete wide range tapping saddle, DN 80 mm(3") with 60 mm( 2") threaded outlet, including gaskets, bolts, and nuts | Piece | 36 | 24,65 | 887,40 |
| 56 | Complete wide range tapping saddle, DN 80 mm(3") with DN 25 mm ( 1") threaded outlet including gaskets, bolts and nuts | Piece | 78 | 23,53 | 1.835,34 |
| 57 | Complete wide range tapping saddle, DN 80 mm(3") with DN 20 mm(3/4")threaded outlet including gaskets, bolts and nuts | Piece | 230 | 23,53 | 5.411,90 |
| 58 | Complete wide range tapping saddle, DN 100 mm(4") with DN 60mm (2") threaded outlet including gaskets, bolts and nuts | Piece | 27 | 24,20 | 653,40 |
| 59 | Complete wide range tapping saddle, DN 100 mm(4") with DN 25 mm (1") threaded outlet including gaskets, bolts and nuts | Piece | 312 | 24,20 | 7.550,40 |
| 60 | Pressure reducing valve, DN 50 mm(2") to reduce the pressure from 25 bars to 10 bars | Piece | 7 | 950,58 | 6.654,06 |
| 61 | Electro-fusion welding machine and accessories (set of 2 ) to weld HDPE | Piece | 3 | 3.383,37 | 10.150,11 |
| 62 | Tapping machine to make threaded outlets for connection from 1/2" to 2" on ductile iron pipes | Piece | 3 | 3.080,46 | 9.241,38 |
| TOTAL |  |  | 437.725,97 |

Annex 7. Trainings

Not applicable

ANNEX 8. Backers Interventions

Interventions of other backers for the same project or for project pursuing the same specific objective.

| Bailleurs de fonds intervenant dans le même projet |
| --- |
| Backers | Name of the Intervention | Budget | Main objectives | Comments |
| Not Applicable |  |  |  |  |
| Bailleurs de fonds contribuant à un même objectif spécifique |
| Backers | Name of the Intervention | Budget | Main objectives | Comments |
| Not Applicable |  |  |  |  |

# Footnotes

According to PRIMA, §70, p.19, it is a matter "of appreciating if the choices regarding to the objectives, the target groups and the local execution organs remain relevant and consistent according to the general principles of a useful and efficient aid, and according to the execution of the local, regional, international and Belgian development policies and strategies".

According to PRIMA, §71, pp. 19-20, it is a matter of "appreciate and measure the foreseen performances agreed during the preparation traineeships according to the 4 criteria and the indicators established during the formulation. (The 4 criteria are efficiency, suitability, respect of deadlines and quality of the personnel)".

See annex 1 for further information